## Week 1 - Initial Plan
Unit 9 Gantt Chart
UNIT 9 Gantt Chart | [22 empty] | Key: |  |  | Completed |  |  |  |  | Started |  |  |  | Deadline
TASK NUMBER | TASK TITLE | TASK COMPLETION | PHASE ONE (Brief Analysis) | [6 empty] | PHASE TWO (Easter Break - Research) | [13 empty] | PHASE THREE (Implementation) | [13 empty] | PHASE FOUR
|  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6
|  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W
1 | Requirements / Brief Analaysis
1.1 | Requirements | 0%
1.2 | Mind Maps | 0%
1.3 | Risk Assessment | 0%
1.4 | Mood boards | 0%
1.5 | Feasability Study | 0%
2 | Planning
2.1 | Gantt Chart | 0%
2.2 | Reflective diary | 0%
3 | Research
3.1 | Purpose of website | 0%
3.2 | Target Audience Profile | 0%
3.3 | Performance Factors | 0%
3.4 | Accessibility | 0%
3.5 | Layout/Whitespace | 0%
3.6 | Typography | 0%
3.7 | SEO | 0%
3.8 | Javascript / Server side script | 0%
3.91 | Performance Factors | 0%
3.92 | Evaluation | 0%
4 | Design
4.1 |  | 0%
4.2 |  | 0%
4.3 |  | 0%
4.4 |  | 0%
4.5 |  | 0%
4.6 |  | 0%
4.7 |  | 0%
4.8 |  | 0%
5 | Design Review
5.1 |  | 0%
5.2 |  | 0%
5.3 |  | 0%
5.4 |  | 0%
5.5 |  | 0%
6 | Pre Production (Implementation)
6.1 |  | 0%
6.2 |  | 0%
6.3 |  | 0%
6.4 |  | 0%
7 | Production (Implementation)
7.1 |  | 0%
7.2 |  | 0%
8
8.1 |  | 0%
8.2 |  | 0%
9 | Testing / Review
9.1 |  | 0%
9.2 |  | 0%
10 | Evaluation
10.1 |  | 0%
10.2 |  | 0%
10.3 |  | 0%
10.4 |  | 0%
10.5 |  | 0%
10.6 |  | 0%
10.7 |  | 0%

## Week 6 - Research Review
Unit 9 Gantt Chart | [24 empty] | A |  |  |  |  | A |  |  |  | A | [5 empty] | A
UNIT 9 Gantt Chart | [22 empty] | Key: |  |  | Completed |  |  |  |  | Started |  |  |  | Planned finish | [5 empty] | Planned Start | [5 empty] | Planned progression
TASK NUMBER | TASK TITLE | TASK COMPLETION
|  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17
|  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
 | time axis 2019-09-16 to 2020-01-10
1 | Requirements / Brief Analaysis
1.1 | Requirements | 0% | bar: 2019-09-17 to 2019-09-18
1.2 | Mind Maps | 0% | bar: 2019-09-17
1.3 | Risk Assessment | 0% | bar: 2019-09-18
1.4 | Mood boards | 0% | bar: 2019-09-18
1.5 | Feasability Study | 0%
2 | Planning
2.1 | Gantt Chart | 0%
2.2 | Reflective diary | 0%
3 | Research
3.1 | Purpose of website | 0% | bar: 2019-09-28; 2019-10-02; 2019-10-15
3.2 | Target Audience Profile | 0% | bar: 2019-10-02; 2019-10-08; 2019-10-15
3.3 | Performance Factors | 0% | bar: 2019-09-28; 2019-10-02; 2019-10-08; 2019-10-15
3.4 | Accessibility | 0% | bar: 2019-09-28; 2019-09-30; 2019-10-02; 2019-10-08; 2019-10-15
3.5 | Layout/Whitespace | 0% | bar: 2019-10-15; 2019-10-18
3.6 | Typography / Multimedia | 0% | bar: 2019-09-30; 2019-10-02; 2019-10-08; 2019-10-15
3.7 | SEO | 0% | bar: 2019-10-02; 2019-10-08; 2019-10-15
3.8 | Javascript / Server side script | 0% | bar: 2019-10-02 to 2019-10-03; 2019-10-08; 2019-10-15
3.91 | Performance Factors | 0% | bar: 2019-10-02 to 2019-10-03; 2019-10-08; 2019-10-15
3.92 | Evaluation | 0% | bar: 2019-10-08; 2019-10-10; 2019-10-12; 2019-10-15; 2019-10-18
4 | Design
4.1 |  | 0%
4.2 |  | 0%
4.3 |  | 0%
4.4 |  | 0%
4.5 |  | 0%
4.6 |  | 0%
4.7 |  | 0%
4.8 |  | 0%
5 | Design Review
5.1 |  | 0%
5.2 |  | 0%
5.3 |  | 0%
5.4 |  | 0%
5.5 |  | 0%
6 | Pre Production (Implementation)
6.1 |  | 0%
6.2 |  | 0%
6.3 |  | 0%
6.4 |  | 0%
7 | Production (Implementation)
7.1 |  | 0%
7.2 |  | 0%
8
8.1 |  | 0%
8.2 |  | 0%
9 | Testing / Review
9.1 |  | 0%
9.2 |  | 0%
10 | Evaluation
10.1 |  | 0%
10.2 |  | 0%
10.3 |  | 0%
10.4 |  | 0%
10.5 |  | 0%
10.6 |  | 0%
10.7 |  | 0%

## Week 9 - End of design phase
Unit 9 Gantt Chart
UNIT 9 Gantt Chart | [22 empty] | Key: |  |  | Completed |  |  |  |  | Started |  |  |  | Planned finish | [5 empty] | Planned Start | [5 empty] | Planned progression | [7 empty] | Undoable date
TASK NUMBER | TASK TITLE | TASK COMPLETION | Phase one | [6 empty] | Phase two | [27 empty] | Phase three
|  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17
|  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
 | time axis 2019-09-16 to 2020-01-10
1 | Requirements / Brief Analaysis
1.1 | Requirements | 100% | bar: 2019-09-17 to 2019-09-18; 2019-12-03 to 2020-01-10
1.2 | Mind Maps | 100% | bar: 2019-09-17; 2019-12-03 to 2020-01-10
1.3 | Risk Assessment | 100% | bar: 2019-09-17 to 2019-09-18; 2019-12-03 to 2020-01-10
1.4 | Mood boards | 100% | bar: 2019-09-17 to 2019-09-18; 2019-12-03 to 2020-01-10
2 | Planning
2.1 | Gantt Chart | 50% | bar: 2019-09-16 to 2019-09-17; 2019-09-19; 2019-10-22; 2019-11-12; 2019-12-01; 2019-12-03 to 2020-01-10
2.2 | Reflective diary | 50% | bar: 2019-09-16 to 2019-09-17; 2019-09-19; 2019-10-22; 2019-11-12; 2019-12-01; 2019-12-03 to 2020-01-10
2.3 | Feasability Study | 87% | bar: 2019-09-17 to 2019-09-18; 2019-12-03 to 2020-01-10
3 | Research
3.1 | Purpose of website | 100% | bar: 2019-09-28; 2019-10-02; 2019-10-15; 2019-12-03 to 2020-01-10
3.2 | Target Audience Profile | 100% | bar: 2019-10-02; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.3 | Performance Factors | 100% | bar: 2019-09-28; 2019-10-02; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.4 | Accessibility | 100% | bar: 2019-09-28; 2019-09-30; 2019-10-02; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.5 | Layout/Whitespace | 0% | bar: 2019-10-15; 2019-10-18; 2019-12-03 to 2020-01-10
3.6 | Typography / Multimedia | 100% | bar: 2019-09-30; 2019-10-02; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.7 | SEO | 100% | bar: 2019-10-02; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.8 | Javascript / Server side script | 100% | bar: 2019-10-02 to 2019-10-03; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.91 | Performance Factors | 100% | bar: 2019-10-02 to 2019-10-03; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.92 | Evaluation | 100% | bar: 2019-10-08; 2019-10-10; 2019-10-12; 2019-10-15; 2019-10-18; 2019-12-03 to 2020-01-10
4 | Design
4.1 | Look into appropriate colour scheme | 100% | bar: 2019-10-22; 2019-11-03; 2019-12-03 to 2020-01-10
4.2 | Find fonts for the website | 100% | bar: 2019-10-22; 2019-11-03; 2019-12-03 to 2020-01-10
4.3 | Design two mockups | 100% | bar: 2019-10-22; 2019-11-04; 2019-12-03 to 2020-01-10
4.4 | Find assets to use | 100% | bar: 2019-10-22; 2019-11-03; 2019-12-03 to 2020-01-10
5 | Design Review
5.1 | Design a questionairre | 100% | bar: 2019-11-05; 2019-11-07; 2019-12-03 to 2020-01-10
5.2 | Peer review | 100% | bar: 2019-11-07; 2019-11-09; 2019-11-12; 2019-12-03 to 2020-01-10
5.3 | Improvements | 100% | bar: 2019-11-12 to 2019-11-13; 2019-12-03 to 2020-01-10
6 | Pre production
6.1 | Wireframe | 100% | bar: 2019-11-05; 2019-11-07; 2019-11-14; 2019-11-16; 2019-12-03 to 2020-01-10
6.2 | Content | 100% | bar: 2019-11-05; 2019-11-07; 2019-11-14; 2019-11-16; 2019-12-03 to 2020-01-10
6.3 | Images | 100% | bar: 2019-11-05; 2019-11-07; 2019-11-14; 2019-11-16; 2019-12-03 to 2020-01-10
6.4 | Assets | 100% | bar: 2019-11-05; 2019-11-07; 2019-11-14; 2019-11-16; 2019-12-03 to 2020-01-10
6.5 | Flow Diagrams | 100% | bar: 2019-11-05 to 2019-11-06; 2019-11-14; 2019-11-16; 2019-12-03 to 2020-01-10
7 | Production
7.1 | Website Template | 100% | bar: 2019-11-16; 2019-11-20; 2019-12-03 to 2020-01-10
| Home | 100% | bar: 2019-11-16; 2019-12-03 to 2020-01-10
| About | 100% | bar: 2019-11-16; 2019-12-03 to 2020-01-10
| Events | 100% | bar: 2019-11-16; 2019-12-03 to 2020-01-10
| Contact | 100% | bar: 2019-11-16; 2019-12-03 to 2020-01-10
8 | Post-Production
8.1 | Scripting | 100% | bar: 2019-11-20 to 2019-11-21; 2019-12-03 to 2020-01-10
8.2 | Optimisation | 100% | bar: 2019-11-20 to 2019-11-21; 2019-12-03 to 2020-01-10
8.3 | Mobile Site | 0% | bar: 2019-11-20 to 2019-11-21; 2019-12-03 to 2020-01-10
9 | Testing / Review
9.1 | Test Plan | 100% | bar: 2019-11-21; 2019-11-23; 2019-12-03 to 2020-01-10
9.2 | Peer Test | 100% | bar: 2019-11-21; 2019-11-23; 2019-12-03 to 2020-01-10
10 | Evaluation
10.1 |  | 1% | bar: 2019-11-26 to 2019-11-27; 2019-12-03 to 2020-01-10

## Week 11 - End of Project
Unit 9 Gantt Chart
UNIT 9 Gantt Chart | [22 empty] | Key: |  |  | Completed |  |  |  |  | Started |  |  |  | Planned finish | [5 empty] | Planned Start | [5 empty] | Planned progression | [7 empty] | Undoable date
TASK NUMBER | TASK TITLE | TASK COMPLETION | Phase one | [6 empty] | Phase two | [27 empty] | Phase three
|  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13 | [6 empty] | WEEK 14 | [6 empty] | WEEK 15 | [6 empty] | WEEK 16 | [6 empty] | WEEK 17
|  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F
 | time axis 2019-09-16 to 2020-01-10
1 | Requirements / Brief Analaysis
1.1 | Requirements | 100% | bar: 2019-09-17 to 2019-09-18; 2019-12-03 to 2020-01-10
1.2 | Mind Maps | 100% | bar: 2019-09-17; 2019-12-03 to 2020-01-10
1.3 | Risk Assessment | 100% | bar: 2019-09-17 to 2019-09-18; 2019-12-03 to 2020-01-10
1.4 | Mood boards | 100% | bar: 2019-09-17 to 2019-09-18; 2019-12-03 to 2020-01-10
2 | Planning
2.1 | Gantt Chart | 50% | bar: 2019-09-16 to 2019-09-17; 2019-09-19; 2019-10-22; 2019-11-12; 2019-12-03 to 2020-01-10
2.2 | Reflective diary | 50% | bar: 2019-09-16 to 2019-09-17; 2019-09-19; 2019-10-22; 2019-11-12; 2019-12-03 to 2020-01-10
2.3 | Feasability Study | 87% | bar: 2019-09-17 to 2019-09-18; 2019-12-03 to 2020-01-10
3 | Research
3.1 | Purpose of website | 100% | bar: 2019-09-28; 2019-10-02; 2019-10-15; 2019-12-03 to 2020-01-10
3.2 | Target Audience Profile | 100% | bar: 2019-10-02; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.3 | Performance Factors | 100% | bar: 2019-09-28; 2019-10-02; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.4 | Accessibility | 100% | bar: 2019-09-28; 2019-09-30; 2019-10-02; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.5 | Layout/Whitespace | 0% | bar: 2019-10-15; 2019-10-18; 2019-12-03 to 2020-01-10
3.6 | Typography / Multimedia | 100% | bar: 2019-09-30; 2019-10-02; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.7 | SEO | 100% | bar: 2019-10-02; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.8 | Javascript / Server side script | 100% | bar: 2019-10-02 to 2019-10-03; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.91 | Performance Factors | 100% | bar: 2019-10-02 to 2019-10-03; 2019-10-08; 2019-10-15; 2019-12-03 to 2020-01-10
3.92 | Evaluation | 100% | bar: 2019-10-08; 2019-10-10; 2019-10-12; 2019-10-15; 2019-10-18; 2019-12-03 to 2020-01-10
4 | Design
4.1 | Look into appropriate colour scheme | 100% | bar: 2019-10-22; 2019-11-03; 2019-12-03 to 2020-01-10
4.2 | Find fonts for the website | 100% | bar: 2019-10-22; 2019-11-03; 2019-12-03 to 2020-01-10
4.3 | Design two mockups | 100% | bar: 2019-10-22; 2019-11-04; 2019-12-03 to 2020-01-10
4.4 | Find assets to use | 100% | bar: 2019-10-22; 2019-11-03; 2019-12-03 to 2020-01-10
5 | Design Review
5.1 | Design a questionairre | 100% | bar: 2019-11-05; 2019-11-07; 2019-12-03 to 2020-01-10
5.2 | Peer review | 100% | bar: 2019-11-07; 2019-11-09; 2019-11-12 to 2019-11-13; 2019-12-03 to 2020-01-10
5.3 | Improvements | 100% | bar: 2019-11-12 to 2019-11-13; 2019-11-21; 2019-12-03 to 2020-01-10
6 | Pre production
6.1 | Wireframe | 100% | bar: 2019-11-05; 2019-11-07; 2019-11-14; 2019-11-16; 2019-12-03 to 2020-01-10
6.2 | Content | 100% | bar: 2019-11-05; 2019-11-07; 2019-11-14; 2019-11-16; 2019-12-03 to 2020-01-10
6.3 | Images | 100% | bar: 2019-11-05; 2019-11-07; 2019-11-14; 2019-11-16; 2019-12-03 to 2020-01-10
6.4 | Assets | 100% | bar: 2019-11-05; 2019-11-07; 2019-11-14; 2019-11-16; 2019-12-03 to 2020-01-10
6.5 | Flow Diagrams | 100% | bar: 2019-11-05 to 2019-11-06; 2019-11-14; 2019-11-16; 2019-12-03 to 2020-01-10
7 | Production
7.1 | Website Template | 100% | bar: 2019-11-16; 2019-11-19 to 2019-11-20; 2019-12-01; 2019-12-03 to 2020-01-10
| Home | 100% | bar: 2019-11-16; 2019-11-20; 2019-12-01; 2019-12-03 to 2020-01-10
| About | 100% | bar: 2019-11-16; 2019-11-20; 2019-12-01; 2019-12-03 to 2020-01-10
| Events | 100% | bar: 2019-11-16; 2019-11-20; 2019-12-01; 2019-12-03 to 2020-01-10
| Contact | 100% | bar: 2019-11-16; 2019-11-20; 2019-12-01; 2019-12-03 to 2020-01-10
8 | Post-Production
8.1 | Scripting | 100% | bar: 2019-11-20 to 2019-11-21; 2019-12-01; 2019-12-03 to 2020-01-10
8.2 | Optimisation | 100% | bar: 2019-11-20 to 2019-11-21; 2019-12-01; 2019-12-03 to 2020-01-10
8.3 | Mobile Site | 0% | bar: 2019-11-20 to 2019-11-21; 2019-12-03 to 2020-01-10
9 | Testing / Review
9.1 | Test Plan | 100% | bar: 2019-11-21; 2019-11-23; 2019-12-01; 2019-12-03 to 2020-01-10
9.2 | Peer Test | 100% | bar: 2019-11-21; 2019-11-23; 2019-12-03 to 2020-01-10
10 | Evaluation
10.1 |  | 100% | bar: 2019-11-26 to 2019-11-27; 2019-12-03 to 2020-01-10